## Backlog
User Story | Story Points | Sprint | Start Date | Status | Note
As as business owner I should be able to see my all emails leads in his inbox | 5 | Sprint 1 | 2016-02-22
As a user I should be able to see lead details in email body format | 2 | Sprint 1
As a user I should be able to see list of products associated with customer | 3 | Sprint 1
I should be able to search products by selecting or double clicking product name from email body text | 3 | Sprint 1
As a user I should be able to see the last purchased variant of the product I select on the top of suggetion list | 9 | Sprint 2 | 2016-02-29
As user I should be able to add the selected product in order list along with quantity | 3 | Sprint 2
As a user I should be able to create order with selected products, expected delivery date, state and assign to | 5 | Sprint 2
As a user I should be able to see all the orders in my inbox | 5 | Sprint 3 | 2016-03-07
As a user I should be able to preview and edit order details | 5 | Sprint 3
As a delivery manager I should be able to see all the orders assigned to me | 3 | Sprint 3
As a delivery manager I should be able to update the order status of my assigned orders | 3 | Sprint 3
2016-03-14